leadership mtg — Sun 27 Sep 2026 — 9:05am-10:50am, board rm Shuwaikh

present: Dana (chair), Faisal, Noura, Sara, Omar, Yousef. notes: Hind (CEO office). Omar joined late ~9:20

1) H1 / Aug numbers

- Faisal: delivery app rev up a lot (92k Jan -> 148k Aug) BUT op costs up faster since May. driver pay + platform fees. Aug margin approx -3%, first negative month

- Dana: so we grow and lose money on each order?? need fix before Q4

- wholesale July dip ~21% vs June. Yousef says hotels quiet in summer + 2 hotels paused orders (renovation). Aug partly back

- Noura: top 5 hotel clients = ~31% of wholesale. risky. Dana agrees, wants plan

- cafes fine, growing ~2%/mo, sat 4.6ish

2) POS upgrade

- Omar: Fahaheel POS tickets spiked in Aug after firmware 4.2. terminals froze, card payments failed. rolled back some, still issues

- Omar asks for full upgrade all 6 cafes + integration w/ delivery app. budget 120k (in board pack)

- pilot Salmiya first. Yousef ok but NOT during cold brew launch wk (18 Oct)

- DECISION: go ahead w/ pilot at Salmiya, start Sun 25 Oct. full rollout Nov-Dec subject to board approval

- Yousef: no more auto firmware updates until IT tests at 1 cafe. Omar ok

3) Delivery app fees

- Faisal: 2 options for new fee model: (a) customer delivery fee 0.500 KWD on orders under 5 KWD, (b) renegotiate partner commission from 22% -> 17%. prob both

- Sara worried (a) hurts app growth / new users

- DECISION: pause all new delivery promo codes until fee model agreed. existing promos run to end Oct

- open Q: who leads partner negotiation — Faisal or Yousef? not agreed

4) Cold brew launch (18 Oct)

- Sara: budget 18k (Insta 4.5k, TikTok 4k, influencers 3k, Snap 2.5k, in-cafe 2.5k, email 0.5k, contingency 1k)

- Faisal: too much given delivery margin. wants 12k, drop influencers + cut TikTok. "we can do in-cafe + Insta only"

- Sara disagrees strongly — TikTok + creators = how we reach 22-35. without them target 25k bottles not realistic

- Dana: not deciding today. both bring options to board

- open Q: final cold brew budget 18k or 12k?

5) Sales / Darwaza Hotels

- Noura: Darwaza Hotels (4 hotels) ~70k/yr, decision by 30 Nov, start Jan. current supplier late deliveries

- DECISION: Noura leads Darwaza proposal, 3 price tiers ok (Classic / Premium / Signature)

- Khalid lost a lot of deals on price this yr — Noura to look at discount rules. (not an action yet?)

6) AOB

- Faisal: POS 102k already in Q4 capex so cash ok

- Jahra cafe weekend hours — keep late opening Thu/Fri? no data. open Q

- wholesale July dip — one-off (summer) or trend? Yousef thinks one-off. Dana wants proof. open Q

ACTIONS

- Faisal — delivery fee model options (a)+(b) w/ numbers for board pack — by Thu 1 Oct

- Omar — POS pilot plan + vendor contract for Salmiya — next wk

- Noura — Darwaza proposal draft to Dana — 15 Oct

- Sara — cold brew budget, 2 options (18k / 12k) + impact on targets — before board

- Yousef — wholesale July dip analysis + call top 5 hotel clients — end of month-ish

next mtg Sun 4 Oct same time. board mtg date tbc (mid Oct?)