# Project Plan: POS Upgrade for Tamra Cafés

Tamra Foods Co. — IT department. Project owner: Omar Al-Enezi, Head of IT. Version 1.0, September 2026.

# Why we need this project

Our point-of-sale (POS) terminals are more than six years old. They fail more often, and they do not connect to the delivery app. Staff must type app orders into the POS by hand.

POS terminal faults are one of the largest groups of IT tickets from the cafés.

In August 2026, Fahaheel logged 13 POS tickets. Many started after the firmware 4.2 update: terminals froze and card payments failed.

App orders typed by hand cause mistakes and slow service at peak times.

The vendor will stop supporting the old terminals at the end of 2027.

# Scope

## In scope

New POS terminals and card readers in all six cafés (Sharq, Salmiya, Hawally, Jabriya, Fahaheel, Jahra).

Kitchen display screens in every café.

Integration with the Tamra delivery app, so app orders go straight to the POS and the kitchen screen.

Staff training and a support plan.

## Out of scope

Warehouse and head office systems.

Changes to the delivery app for customers.

# Phases and timeline

| Phase | Dates (2026) | What happens |
| --- | --- | --- |
| 0. Preparation | 4–22 Oct | Final vendor contract, network checks, order hardware |
| 1. Pilot at Salmiya | 25 Oct–12 Nov | Install in Salmiya; run old and new side by side for one week |
| 2. Pilot review | 15–19 Nov | Check results; fix issues; go / no-go decision |
| 3. Rollout wave 1 | 22 Nov–3 Dec | Fahaheel, Sharq, Hawally |
| 4. Rollout wave 2 | 6–17 Dec | Jabriya, Jahra |
| 5. Close | 20–31 Dec | Remove old terminals; final report |

We install at night, after the café closes, so trading is not affected. Fahaheel is first in wave 1 because it had the most faults.

# Budget: KWD 120,000

| Item | Detail | KWD |
| --- | --- | --- |
| POS terminals and card readers | 36 units × KWD 1,650 | 59,400 |
| Kitchen display screens | 12 units × KWD 900 | 10,800 |
| Software licences (year 1) | 36 licences | 14,400 |
| Delivery app integration | Vendor development and testing | 16,000 |
| Installation and network work | 6 cafés | 7,200 |
| Training | Trainer time and materials | 4,200 |
| Contingency | About 7% | 8,000 |
| Total |  | 120,000 |

# Risks and mitigations

| Risk | Impact | Mitigation |
| --- | --- | --- |
| New terminals fail during a busy shift | High | Keep old terminals as backup for 2 weeks in each café |
| Firmware problems like the August 4.2 update | High | Test every update at Salmiya first; no automatic updates |
| Delivery app integration is late | Medium | Pilot can start without integration; add it before wave 1 |
| Staff are not confident with the new system | Medium | Train every shift; one “POS champion” per café |
| Hardware arrives late | Medium | Order in week 1; vendor has stock in Kuwait |
| Budget overrun | Low | KWD 8,000 contingency; monthly cost check with Finance |

# Support and training plan

Two-hour hands-on training for every café team before go-live.

One POS champion per café as the first contact for questions.

IT support on site for the first three days in each café.

Help desk: P1 POS tickets answered within 30 minutes, 7 days a week.

Short how-to videos in English and Arabic.

# Success measures

| Measure | Today | Target by March 2027 |
| --- | --- | --- |
| POS tickets per café per month | About 5 | 2 or fewer |
| App orders typed by hand | All | None |
| Average checkout time | 95 seconds | 60 seconds |
| Order errors on app orders | About 3% | Under 1% |
| Staff who feel confident with the POS | — | 90% or more |

Contact: it.support@tamrafoods.example